## Sheet1
CR Description | Start | Task ID
SEG-1-DAL-POD3&4-SDL-CPIO Deployment on Staging VNF | 2026-06-02 | 124
SEG-1-ELG-POD3&4-SDL-CPIO Deployment on Staging VNF | 2026-06-03 | 125
SEG-1-NVL-POD3&4-SDL-CPIO Deployment on Staging VNF | 2026-06-03 | 126
SEG-1-DAL-POD3&4-PGW-CPIO Deployment on Staging VNF | 2026-06-23 | 127
SEG-1-ELG-POD3&4-PGW-CPIO Deployment on Staging VNF | 2026-06-24 | 128
SEG-1-NVL-POD3&4-PGW-CPIO Deployment on Staging VNF | 2026-06-25 | 129
SEG-1-ELG-POD3&4-SDL-VNF Shutdown for Resilience Testing with ANB - MW1 (Post Migration) | 2026-06-24 | 202
SEG-1-ELG-POD3&4-SDL-VNF Shutdown for Resilience Testing with ANB - MW2 (Post Migration) | 2026-06-25 | 203
SEG-1-ELG-POD3&4-INFRA FailOver Testing - MW1 (Post Migration) | 2026-06-26 | 204
SEG-1-ELG-POD3&4-INFRA FailOver Testing - MW2 (Post Migration) | 2026-06-29 | 205
SEG-2-DAL/ELG/NVL-POD7&8-NDS1 > SDL2 Subscriber Migration MW23 ~ 1M (DAY_MW) | 2026-05-20 | 515
SEG-2-DAL/ELG/NVL-POD7&8-NDS1 > SDL2 Subscriber Migration MW23~ 1M CLEAN-UP | 2026-05-20 | 516
SEG-2-DAL/ELG/NVL-POD7&8-NDS1 > SDL2 Subscriber Migration MW24 ~ 1M (DAY_MW) | 2026-05-25 | 517
SEG-2-DAL/ELG/NVL-POD7&8-NDS1 > SDL2 Subscriber Migration MW24 ~ 1M CLEAN-UP | 2026-05-25 | 518
SEG-3-DAL-POD12-SDL-VNF Shutdown for Resilience Testing with ANB - MW1 (Pre-Migration) | 2026-06-01 | 554
SEG-3-DAL-POD12-SDL-VNF Shutdown for Resilience Testing with ANB - MW2 (Pre-Migration) | 2026-06-01 | 555
SEG-3-DAL-POD12-INFRA FailOver Testing - MW1 (Pre-Migration) | 2026-06-03 | 556
SEG-3-DAL-POD12-INFRA FailOver Testing - MW2 (Pre-Migration) | 2026-06-03 | 557
SEG-3-ELG-POD12-SDL-VNF Shutdown for Resilience Testing with ANB - MW1 (@ 10M Active) | 2026-07-08 | 558
SEG-3-ELG-POD12-SDL-VNF Shutdown for Resilience Testing with ANB - MW2 (@ 10M Active) | 2026-07-08 | 559
SEG-3-ELG-POD12-INFRA FailOver Testing - MW1 (@ 10M Active) | 2026-07-13 | 560
SEG-3-ELG-POD12-INFRA FailOver Testing - MW2 (@ 10M Active) | 2026-07-13 | 561
SEG-3-NVL-POD12-SDL-VNF Shutdown for Resilience Testing with ANB - MW1 (Post Migration) | 2026-07-20 | 562
SEG-3-NVL-POD12-SDL-VNF Shutdown for Resilience Testing with ANB - MW2 (Post Migration) | 2026-07-22 | 563
SEG-3-NVL-POD12-INFRA FailOver Testing - MW1 (Post Migration) | 2026-07-22 | 564
SEG-3-NVL-POD12-INFRA FailOver Testing - MW2 (Post Migration) | 2026-07-23 | 565
SEG-3-POD12-Global SYNC Config Service DISABLE towards NDS1 + 1 Day SOAK | 2026-06-24 | 625
SEG-3-POD12-DAL-Provisioning DISABLE between SDL3 & NDS1 | 2026-06-25 | 626
SEG-3-POD12-ELG-Provisioning DISABLE between SDL3 & NDS1 | 2026-06-28 | 627
SEG-3-POD12-NVL-Provisioning DISABLE between SDL3 & NDS1 | 2026-06-29 | 628
SEG-LU-POD15-SEGMENT ID update in SDL Lookup IMSI TABLE & Set Priority Flag(SEG-3 Migration Ranges) | 2026-05-19 | 640
SEG-3-DAL/ELG/NVL-POD12-NDS1 > SDL3 Subscriber Migration MW1 ~ 12K (NIGHT_MW) | 2026-06-16 | 645
SEG-3-DAL/ELG/NVL-POD12-NDS1 > SDL3 Subscriber Migration MW2 ~ 108K (NIGHT_MW) | 2026-06-17 | 646
SEG-3-DAL/ELG/NVL-POD12-NDS1 > SDL3 Subscriber Migration MW3 ~ 268K (NIGHT_MW) | 2026-06-21 | 647
SEG-3-DAL/ELG/NVL-POD12-NDS1 > SDL3 Subscriber Migration MW4 ~ 660K (NIGHT_MW) | 2026-06-23 | 648
SEG-3-DAL/ELG/NVL-POD12-NDS1 > SDL3 Subscriber Migration Cleanup - ACTIVE | 2026-06-26 | 651
SEG-3-DAL/ELG/NVL-POD12-NDS1 > SDL3 Subscriber Migration Cleanup - Pre-Prov | 2026-06-28 | 652
SEG-3-DAL/ELG/NVL-POD12-NDS1 > SDL3 Subscriber Migration MW5 ~ 933 (DAY_MW) | 2026-06-29 | 654
SEG-3-DAL/ELG/NVL-POD12-NDS1 > SDL3 Subscriber Migration MW6 ~ 7.8M (DAY_MW) | 2026-06-30 | 655
SEG-3-DAL/ELG/NVL-POD12-NDS1 > SDL3 Subscriber Migration MW6 ~ 7.8M CLEAN-UP | 2026-06-30 | 656
SEG-3-DAL/ELG/NVL-POD12-NDS1 > SDL3 Subscriber Migration MW7 ~ 3.7M (DAY_MW) | 2026-07-02 | 657
SEG-3-DAL/ELG/NVL-POD12-NDS1 > SDL3 Subscriber Migration MW7 ~ 3.7M CLEAN-UP | 2026-07-02 | 658
SEG-3-DAL/ELG/NVL-POD12-NDS1 > SDL3 Subscriber Migration MW8 ~ 3.6M (DAY_MW) | 2026-07-06 | 659
SEG-3-DAL/ELG/NVL-POD12-NDS1 > SDL3 Subscriber Migration MW8 ~ 3.6M CLEAN-UP | 2026-07-06 | 660
SEG-3-DAL/ELG/NVL-POD12-NDS1 > SDL3 Subscriber Migration MW9 ~ 2.7M (DAY_MW) | 2026-07-07 | 661
SEG-3-DAL/ELG/NVL-POD12-NDS1 > SDL3 Subscriber Migration MW9 ~ 2.7M CLEAN-UP | 2026-07-07 | 662
SEG-3-DAL/ELG/NVL-POD12-NDS1 > SDL3 Subscriber Migration MW10 ~ 2.3M (DAY_MW) | 2026-07-09 | 664
SEG-3-DAL/ELG/NVL-POD12-NDS1 > SDL3 Subscriber Migration MW10 ~ 2.3M CLEAN-UP | 2026-07-09 | 665
SEG-3-DAL/ELG/NVL-POD12-NDS1 > SDL3 Subscriber Migration MW11 ~ 1.9M (DAY_MW) | 2026-07-13 | 666
SEG-3-DAL/ELG/NVL-POD12-NDS1 > SDL3 Subscriber Migration MW11 ~ 1.9M CLEAN-UP | 2026-07-13 | 667
SEG-3-DAL/ELG/NVL-POD12-NDS1 > SDL3 Subscriber Migration MW12 ~ 1.7M (DAY_MW) | 2026-07-14 | 668
SEG-3-DAL/ELG/NVL-POD12-NDS1 > SDL3 Subscriber Migration MW12 ~ 1.7M CLEAN-UP | 2026-07-14 | 669
SEG-3-DAL/ELG/NVL-POD12-NDS1 > SDL3 Subscriber Migration MW13 ~ 1.5M (DAY_MW) | 2026-07-16 | 670
SEG-3-DAL/ELG/NVL-POD12-NDS1 > SDL3 Subscriber Migration MW13 ~ 1.5M CLEAN-UP | 2026-07-16 | 671
SEG-3-DAL/ELG/NVL-POD12-NDS1 > SDL3 Subscriber Migration MW14 ~ 890K (DAY_MW) | 2026-07-20 | 672
SEG-LU-DAL-POD15-NCOM+ Readiness for NTF_v163 & YANG v230 - DAYTIME | 2026-05-26 | 751
SEG-LU-DAL-POD15-vSDL-NTF_v163 & YANG v230 installation w/NCOM+ | 2026-05-26 | 752
SEG-LU-ELG-POD15-NCOM+ Readiness for NTF_v163 & YANG v230 - DAYTIME | 2026-05-27 | 753
SEG-LU-ELG-POD15-vSDL-NTF_v163 & YANG v230 installation w/NCOM+ | 2026-05-27 | 754
SEG-LU-NVL-POD15-NCOM+ Readiness for NTF_v163 & YANG v230 - DAYTIME | 2026-05-28 | 755
SEG-LU-NVL-POD15-vSDL-NTF_v163 & YANG v230 installation w/NCOM+ | 2026-05-28 | 756
SEG-LU-DAL-POD15-vSDL-RTDBv307 installation w/NCOM+ | 2026-06-02 | 759
SEG-LU-ELG-POD15-NCOM+ Readiness for RTDBv307 - DAYTIME | 2026-05-21 | 760
SEG-LU-ELG-POD15-vSDL-RTDBv307 installation w/NCOM+ | 2026-06-03 | 761
SEG-LU-NVL-POD15-NCOM+ Readiness for RTDBv307 - DAYTIME | 2026-05-22 | 762
SEG-LU-NVL-POD15-vSDL-RTDBv307 installation w/NCOM+ | 2026-06-03 | 763
SEG-LU-DAL-POD15-SDL-Import Root CA for TLS_on_SDL_NTF trigger endpoints | 2026-06-02 | 779
SEG-LU-ELG-POD15-SDL-Import Root CA for TLS_on_SDL_NTF trigger endpoints | 2026-06-04 | 780
SEG-LU-NVL-POD15-SDL-Import Root CA for TLS_on_SDL_NTF trigger endpoints | 2026-06-04 | 781
SEG-LU-DAL-POD15-PGW-Enable-TLS Non LDAP for UPG & PPX, Custom Cipher & Prov isolation | 2026-06-24 | 783
SEG-LU-ELG-POD15-PGW-Enable-TLS Non LDAP for UPG & PPX, Custom Cipher & Prov isolation | 2026-06-25 | 784
SEG-LU-NVL-POD15-PGW-Enable-TLS Non LDAP for UPG & PPX, Custom Cipher & Prov isolation | 2026-06-26 | 785
SEG-1-DAL-POD3&4_SDL New Script_1 RPM installation, configuration & scheduling post BRVM RHEL installation | 2026-05-26 | 792
SEG-2-DAL-POD7&8-SDL New Script_1 RPM installation, configuration & scheduling post BRVM RHEL installation | 2025-08-04 | 793
SEG-3-DAL-POD12-SDL New Script_1 RPM installation, configuration & scheduling post BRVM RHEL installation | 2025-08-04 | 794
SEG-LU-DAL-POD15-SDL New Script_1 RPM installation, configuration & scheduling post BRVM RHEL installation | 2025-08-04 | 795
SEG-1-ELG-POD3&4_SDL New Script_1 RPM installation, configuration & scheduling post BRVM RHEL installation | 2025-08-04 | 796
SEG-2-ELG-POD7&8-SDL New Script_1 RPM installation, configuration & scheduling post BRVM RHEL installation | 2025-08-04 | 797
SEG-3-ELG-POD12-SDL New Script_1 RPM installation, configuration & scheduling post BRVM RHEL installation | 2025-08-04 | 798
SEG-LU-ELG-POD15-SDL New Script_1 RPM installation, configuration & scheduling post BRVM RHEL installation | 2025-08-04 | 799
SEG-1-NVL-POD3&4_SDL New Script_1 RPM installation, configuration & scheduling post BRVM RHEL installation | 2025-08-04 | 800
SEG-2-NVL-POD7&8-SDL New Script_1 RPM installation, configuration & scheduling post BRVM RHEL installation | 2025-08-04 | 801
SEG-3-NVL-POD12-SDL New Script_1 RPM installation, configuration & scheduling post BRVM RHEL installation | 2025-08-04 | 802
SEG-LU-NVL-POD15-SDL New Script_1 RPM installation, configuration & scheduling post BRVM RHEL installation | 2025-08-04 | 803
SEG-1-DAL-POD3&4-SDL 25.7PP2 Upgrade - NCOM Readiness (Pre-Checks & Setup) | 2026-07-08 | 940
SEG-2-DAL-POD7&8-SDL 25.7PP2 Upgrade - NCOM Readiness (Pre-Checks & Setup) | 2026-07-08 | 941
SEG-LU-DAL-POD15-SDL 25.7PP2 Upgrade - NCOM Readiness (Pre-Checks & Setup) | 2026-07-08 | 942
SDL 25.7PP2 Upgrade - Prov(A10) Traffic DISABLE | 2026-07-15 | 943
SEG-1-DAL-POD3&4-SDL 25.7PP2 Upgrade w/NCOM+ LDAP & BQR Kafka Ports Block, VNF1,VNF2,VNF9,VNF10 | 2026-07-15 | 945
SEG-1-DAL-POD3&4-SDL 25.7PP2 Upgrade w/NCOM+ VNF1,VNF2,VNF9,VNF10 (ANB, NetAct & Safeguard int) | 2026-07-15 | 946
SEG-1-DAL-POD3&4-SDL 25.7PP2 Upgrade w/NCOM+ VNF3,VNF4,VNF11,VNF12 | 2026-07-16 | 947
SEG-1-DAL-POD3&4-SDL 25.7PP2 Upgrade w/NCOM+ VNF3,VNF4,VNF11,VNF12 (ANB, NetAct & Safeguard int) | 2026-07-16 | 948
SEG-1-DAL-POD3&4-SDL 25.7PP2 Upgrade w/NCOM+ VNF5, VNF6,VNF13,VNF14 | 2026-07-17 | 949
SEG-1-DAL-POD3&4-SDL 25.7PP2 Upgrade w/NCOM+ VNF5, VNF6,VNF13,VNF14 (ANB, NetAct & Safeguard int) | 2026-07-17 | 950
SEG-1-DAL-POD3&4-SDL 25.7PP2 Upgrade w/NCOM+ VNF7, VNF8, VNF15, VNF16 | 2026-07-19 | 951
SEG-1-DAL-POD3&4-SDL 25.7PP2 Upgrade w/NCOM+ VNF7, VNF8, VNF15, VNF16 (ANB, NetAct & Safeguard int) | 2026-07-19 | 952
SEG-1-DAL-POD3&4-SDL 25.7PP2 PGW& SDLAs Upgrade w/NCOM+ MW1 | 2026-07-20 | 953
SEG-1-DAL-POD3&4-SDL 25.7PP2 PGW& SDLAs Upgrade w/NCOM+ ANB, NetAct & Safeguard int - MW1 | 2026-07-20 | 954
SEG-1-DAL-POD3&4-SDL 25.7PP2 PGW& SDLAs Upgrade w/NCOM+ MW2 | 2026-07-21 | 955
SEG-1-DAL-POD3&4-SDL 25.7PP2 PGW& SDLAs Upgrade w/NCOM+ ANB, NetAct & Safeguard int - MW2 | 2026-07-21 | 956
SEG-1-DAL-POD3&4-SDL 25.7PP2 Upgrade w/NCOM+ LDAP & BQR Kafka Ports UNBLOCK | 2026-07-21 | 957
SEG-2-DAL-POD7&8-SDL 25.7PP2 Upgrade w/NCOM+ LDAP & BQR Kafka Ports Block, VNF1&VNF8 | 2026-07-15 | 959
SEG-2-DAL-POD7&8-SDL 25.7PP2 Upgrade w/NCOM+ VNF1&VNF8 (ANB, NetAct & Safeguard int) | 2026-07-15 | 960
SEG-2-DAL-POD7&8-SDL 25.7PP2 Upgrade w/NCOM+ VNF2, VNF3, VNF9, VNF10 | 2026-07-16 | 961
SEG-2-DAL-POD7&8-SDL 25.7PP2 Upgrade w/NCOM+ VNF2, VNF3, VNF9, VNF10 (ANB, NetAct & Safeguard int) | 2025-09-01 | 962
SEG-2-DAL-POD7&8-SDL 25.7PP2 Upgrade w/NCOM+ VNF4, VNF5, VNF11, VNF12 | 2026-07-17 | 963
SEG-2-DAL-POD7&8-SDL 25.7PP2 Upgrade w/NCOM+ VNF4, VNF5, VNF11, VNF12 (ANB, NetAct & Safeguard int) | 2026-07-17 | 964
SEG-2-DAL-POD7&8-SDL 25.7PP2 Upgrade w/NCOM+ VNF6, VNF7, VNF13, VNF14 | 2026-07-20 | 965
SEG-2-DAL-POD7&8-SDL 25.7PP2 Upgrade w/NCOM+ VNF6, VNF7, VNF13, VNF14 (ANB, NetAct & Safeguard int) | 2026-07-20 | 966
SEG-2-DAL-POD7&8-SDL 25.7PP2 PGW& SDLAs Upgrade w/NCOM+ MW1 | 2026-07-20 | 967
SEG-2-DAL-POD7&8-SDL 25.7PP2 PGW& SDLAs Upgrade w/NCOM+ ANB, NetAct & Safeguard int - MW1 | 2026-07-20 | 968
SEG-2-DAL-POD7&8-SDL 25.7PP2 PGW& SDLAs Upgrade w/NCOM+ MW2 | 2026-07-21 | 969
SEG-2-DAL-POD7&8-SDL 25.7PP2 PGW& SDLAs Upgrade w/NCOM+ ANB, NetAct & Safeguard int - MW2 | 2026-07-21 | 970
SEG-2-DAL-POD7&8-SDL 25.7PP2 Upgrade w/NCOM+ LDAP & BQR Kafka Ports UNBLOCK | 2026-07-22 | 971
SDL 25.7PP2 Upgrade - Prov(A10) Traffic ENABLE - DAL | 2026-07-22 | 984